## Sheet1
Test Execution Summary — OrangeHRM Manual Testing Project
Tester: M Faizan Khan
Application: OrangeHRM Open Source Demo (opensource-demo.orangehrmlive.com)
Test Period: August 2026
Results by Module
Module | Total Cases | Pass | Fail | Not Executed
Login | 12 | 11 | 1 | 0
PIM | 12 | 11 | 1 | 0
Leave | 12 | 9 | 3 | 0
Total | 36 | 31 | 5 | 0
Defects Found
Bug ID | Title | Severity | Module
BUG_001 | First Name accepts numeric/special characters | Low | PIM
BUG_002 | System allows backdated leave requests | Medium | Leave
BUG_003 | No Approve/Reject action on pending leave requests | High | Leave
BUG_004 | Cached dashboard visible via back button after logout | Medium | Login
Key Observations & Recommendations
- Login module performed strongly; validation and SQL-injection-style input handled correctly. Only failure (BUG_004) is a minor client-side caching issue — server-side session termination confirmed correct.
- PIM module solid overall, with one data-validation gap (BUG_001) on the First Name field.
- Leave module had the highest failure rate, driven by BUG_003 (Approve/Reject actions not found). Flagged for re-verification — may be a demo-environment permission artifact rather than a confirmed defect.
- Recommend: re-verify BUG_003 on a controlled instance; add input validation for PIM First Name; restrict/warn on backdated leave; prevent cached authenticated pages from rendering after logout.